## Master
IO list from programmer | [6 empty] | OQ IO list / Please select "Page" and Cutting
module | sybolic | address | comment | cross ref. |  | Test | Address | Kommentar | Page | Test
-K1 | DI4 | IX_000_MPS | motor protection switch 1 = not o.k. | 0000/3.2 | 1 | IX | .004-K1:DI4 | motor protection switch 1 = not o.k. | .000/3.2 | T2
-K1 | DI2 | IX_000_CB | circuit breakers 1 = not o.k. | 0000/3.4 | 2 | IX | .004-K1:DI2 | circuit breakers 1 = not o.k. | .000/3.4 | T2
-K1 | DI3 | IX_000_OCP | monitoring overload 24VDC 1 = o.k. | 0000/3.7 | 3 | IX | .004-K1:DI3 | monitoring overload 24VDC 1 = o.k. | .000/3.7 | T2
-K1 | DQ0 | QX_001_K4EStopRes | 1 = reset emergency stop | 0001/3.4 | 4 | QX | .004-K1:DQ0 | 1 = reset emergency stop | .001/3.4 | T1
-K1 | DI5 | IX_001_EStopDel | emergency stop delayed 1 = o.k. | 0001/3.7 | 5 | IX | .004-K1:DI5 | emergency stop delayed 1 = o.k. | .001/3.7 | T2
-K1 | DI6 | IX_002_B1ProGuard | protective guarding 1 1 = o.k. | 0002/1.2 | 6 | IX | .004-K1:DI6 | protective guarding 1 1 = o.k. | .002/1.2 | T2
-K1 | DI7 | IX_002_B2ProGuard | protective guarding 2 1 = o.k. | 0002/1.2 | 7 | IX | .004-K1:DI7 | protective guarding 2 1 = o.k. | .002/1.2 | T2
-K1 | (TP) DI8 | IX_002_B3ProGuard | protective guarding 3 1 = o.k. | 0002/1.3 | 8 | IX | .004-K1:(TP) DI8 | protective guarding 3 1 = o.k. | .002/1.3 | T2
-K1 | (TP) DI9 | IX_002_B4ProGuard | protective guarding 4 1 = o.k. | 0002/1.4 | 9 | IX | .004-K1:(TP) DI9 | protective guarding 4 1 = o.k. | .002/1.4 | T2
-T3 | DI3 | IX_003_S1Estop | emergency stop control panel | 0003/2.2 | 10 | IX | .007-T3:DI3 | emergency stop control panel | .003/2.2 | T2
-T3 | DI4/DQ0 | IX_003_S2On | 1 = machine start | 0003/2.4 | 11 | IX | .007-T3:DI4/DQ0 | 1 = machine start | .003/2.4 | T2
-T3 | DI5/DQ1 | IX_003_S3Off | 0 = machine stop | 0003/2.5 | 12 | IX | .007-T3:DI5/DQ1 | 0 = machine stop | .003/2.5 | T2
-K1 | DQ2 | QX_003_P1On | 1 = machine is running | 0003/2.6 | 13 | QX | .004-K1:DQ2 | 1 = machine is running | .003/2.6 | T1
-T3 | DI2 | IX_003_S4JogQ | 1 = reset | 0003/3.2 | 14 | IX | .007-T3:DI2 | 1 = reset | .003/3.2 | T2
-T3 | DI3 | IX_003_S5JogP | 1 = jog + | 0003/3.3 | 15 | IX | .007-T3:DI3 | 1 = jog + | .003/3.3 | T2
-T3 | DI4/DQ0 | IX_003_S6JogN | 0 = jog - | 0003/3.4 | 16 | IX | .007-T3:DI4/DQ0 | 0 = jog - | .003/3.4 | T2
-T3 | DI5/DQ1 | IX_003_X3Plugged | 1 = pluged-in | 0003/3.5 | 17 | IX | .007-T3:DI5/DQ1 | 1 = pluged-in | .003/3.5 | T2
-K20.1 | LED 0 | IX_003_S14JogQ | 1 = reset | 0003/4.2 | 18 | IX | .004-K20.1:LED 0 | 1 = reset | .003/4.2 | T2
-K20.1 | LED 1 | IX_003_S15JogP | 1 = jog + | 0003/4.3 | 19 | IX | .004-K20.1:LED 1 | 1 = jog + | .003/4.3 | T2
-K20.1 | LED 2 | IX_003_S16JogN | 1 = jog - | 0003/4.4 | 20 | IX | .004-K20.1:LED 2 | 1 = jog - | .003/4.4 | T2
-K20.1 | LED 3 | IX_003_X13Plugged | 1 = pluged-in | 0003/4.5 | 21 | IX | .004-K20.1:LED 3 | 1 = pluged-in | .003/4.5 | T2
-K1 | DI0 | IX_007_Q1DrivesA | monitoring main contactor 1 = off | 0007/1.2 | 22 | IX | .004-K1:DI0 | monitoring main contactor 1 = off | .007/1.2 | T2
-K1 | DQ1 | QX_007_K1DrivesA | 1 = release main contactor | 0007/1.2 | 23 | QX | .004-K1:DQ1 | 1 = release main contactor | .007/1.2 | T1
-K1 | DQ7 | QX_007_Watchdog | 1 = watchdog active | 0007/1.5 | 24 | QX | .004-K1:DQ7 | 1 = watchdog active | .007/1.5 | T1
-K20.20 | LED 0 | QX_009_P1Op | warning beacon ready for operation machine on | 0009/1.2 | 25 | QX | .004-K20.20:LED 0 | warning beacon ready for operation machine on | .009/1.2 | T1
-K20.20 | LED 1 | QX_009_P2Mat | warning beacon product infeed min.-backup | 0009/1.3 | 26 | QX | .004-K20.20:LED 1 | warning beacon product infeed min.-backup | .009/1.3 | T1
-K20.20 | LED 2 | QX_009_P3Hold | warning beacon holding position | 0009/1.4 | 27 | QX | .004-K20.20:LED 2 | warning beacon holding position | .009/1.4 | T1
-K1 | DQ3 | QX_009_P4Fault | warning beacon collective fault | 0009/1.6 | 28 | QX | .004-K1:DQ3 | warning beacon collective fault | .009/1.6 | T1
-K20.20 | LED 3 | QX_009_P5Horn | horn | 0009/1.7 | 29 | QX | .004-K20.20:LED 3 | horn | .009/1.7 | T1
-T3 | DI0/TP0 | IX_120_B1RefIni | main shaft reference sensor | 0120/2.3 | 30 | IX | .007-T3:DI0/TP0 | main shaft reference sensor | .120/2.3 | T2
-T3 | DI2 | IX_140_B1CompAir | compressed air 1 = o.k. | 0140/1.2 | 31 | IX | .007-T3:DI2 | compressed air 1 = o.k. | .140/1.2 | T2
-K2.02 | Q0.3 | QX_200_K1PrismVacOn | tube infeed pusher 1 = vacuum | 0200/1.2 | 32 | QX | .140-K2.02:Q0.3 | tube infeed pusher 1 = vacuum | .200/1.2 | T1
-K2.12 | Q1.6 | QX_200_K2TubePusher | tube infeed pusher 1 = insert | 0200/1.3 | 33 | QX | .140-K2.12:Q1.6 | tube infeed pusher 1 = insert | .200/1.3 | T1
-T3 | DI0/TP0 | IX_201_B1MinTubes | tube infeed 0 = min.-backup | 0201/1.3 | 34 | IX | .007-T3:DI0/TP0 | tube infeed 0 = min.-backup | .201/1.3 | T2
-K2.13 | Q1.8 | QX_201_K1TubeStopper | tube infeed stopper 1 1 = close | 0201/1.4 | 35 | QX | .140-K2.13:Q1.8 | tube infeed stopper 1 1 = close | .201/1.4 | T1
-K2.14 | Q1.10 | QX_201_K2TubeStopper | tube infeed stopper 2 1 = open | 0201/1.6 | 36 | QX | .140-K2.14:Q1.10 | tube infeed stopper 2 1 = open | .201/1.6 | T1
-T3 | DI1/TP1 | IX_202_B1PosControl | tube position control 1 = o.k. | 0202/1.3 | 37 | IX | .007-T3:DI1/TP1 | tube position control 1 = o.k. | .202/1.3 | T2
-T4 | DI1/TP1 | IX_250_B1TubePres | tube presence | 0250/1.3 | 38 | IX | .007-T4:DI1/TP1 | tube presence | .250/1.3 | T2
-T4 | DI2 | IX_252_ | reserve | 0252/2.4 | 39 | IX | .007-T4:DI2 | reserve | .252/2.4 | T2
-T4 | DI0/TP0 | IX_252_B1PrintReg | tube print registration | 0252/3.2 | 40 | IX | .007-T4:DI0/TP0 | tube print registration | .252/3.2 | T2
-T4 | DI5/DQ1 | QX_252_Q1MagOn | tube print registration magnet on | 0252/3.7 | 41 | QX | .007-T4:DI5/DQ1 | tube print registration magnet on | .252/3.7 | T1
-T2 | DI0/TP0 | IXD_301_B1RefIni | dosing piston reference sensor | 0301/2.3 | 42 | IXD | .007-T2:DI0/TP0 | dosing piston reference sensor | .301/2.3 | T2
-T2 | DI1/TP1 | IX_301_ | reserve | 0301/2.3 | 43 | IX | .007-T2:DI1/TP1 | reserve | .301/2.3 | T2
-T2 | DI4/DQ0 | IX_301_ | reserve | 0301/2.6 | 44 | IX | .007-T2:DI4/DQ0 | reserve | .301/2.6 | T2
-T2 | DI5/DQ1 | IX_301_ | reserve | 0301/2.7 | 45 | IX | .007-T2:DI5/DQ1 | reserve | .301/2.7 | T2
-K2.08 | Q0.14 | QX_305_K1Open | rotary valve 1 = filling position | 0305/1.2 | 46 | QX | .140-K2.08:Q0.14 | rotary valve 1 = filling position | .305/1.2 | T1
-T2 | DI2 | IXD_305_B11RotaryOpen | rotary valve working position | 0305/1.5 | 47 | IXD | .007-T2:DI2 | rotary valve working position | .305/1.5 | T2
-T2 | DI3 | IXD_305_B12RotaryClose | rotary valve home position | 0305/1.7 | 48 | IXD | .007-T2:DI3 | rotary valve home position | .305/1.7 | T2
-K2.01 | Q0.0 | QX_320_K1Open | shut-off stem 1 = open | 0320/1.2 | 49 | QX | .140-K2.01:Q0.0 | shut-off stem 1 = open | .320/1.2 | T1
-K2.01 | Q0.1 | QX_320_K1Close | shut-off stem 1 = close | 0320/1.3 | 50 | QX | .140-K2.01:Q0.1 | shut-off stem 1 = close | .320/1.3 | T1
-T4 | DI0/TP0 | IX_321_B1RefIni | lifter reference sensor | 0321/2.2 | 51 | IX | .007-T4:DI0/TP0 | lifter reference sensor | .321/2.2 | T2
-T4 | DI1/TP1 | IX_321_ | reserve | 0321/2.3 | 52 | IX | .007-T4:DI1/TP1 | reserve | .321/2.3 | T2
-T4 | DI2 | IX_321_B2_Tubeholder | monitoring tube holder in tube holder carrier filling station | 0321/2.4 | 53 | IX | .007-T4:DI2 | monitoring tube holder in tube holder carrier filling station | .321/2.4 | T2
-T4 | DI4/DQ0 | QX_321_Q1MagOn | lifter filling holding magnet | 0321/3.3 | 54 | QX | .007-T4:DI4/DQ0 | lifter filling holding magnet | .321/3.3 | T1
-K2.06 | Q0.11 | QX_330_K1BlowOff | filling blow off 1 = blow off | 0330/1.2 | 55 | QX | .140-K2.06:Q0.11 | filling blow off 1 = blow off | .330/1.2 | T1
-K2.06 | Q0.10 | QX_330_K2BlowFree | filling blow off 1 =cleaning | 0330/1.3 | 56 | QX | .140-K2.06:Q0.10 | filling blow off 1 =cleaning | .330/1.3 | T1
-T4 | DI4/DQ0 | QX_400_Q1Infeed | product infeed 1 = on | 0400/1.6 | 57 | QX | .007-T4:DI4/DQ0 | product infeed 1 = on | .400/1.6 | T1
-K20.17 | 0 | IW_401_B1FillLevel | fill level monitoring | 0401/1.2 | 58 | IW | .004-K20.17:0 | fill level monitoring | .401/1.2 | T2
-T4 | DI3 | IX_401_B2Overfill | overfill protection 0 = super max. | 0401/1.5 | 59 | IX | .007-T4:DI3 | overfill protection 0 = super max. | .401/1.5 | T2
-T3 | DI1/TP1 | IX_401_B3SensorWorkPos | fill level monitoring swivel arm 1 = in position | 0401/1.7 | 60 | IX | .007-T3:DI1/TP1 | fill level monitoring swivel arm 1 = in position | .401/1.7 | T2
-K1 | (TP) DI10 | IX_500_B1WaterOK | cooling water 1 = o.k. | 0500/1.7 | 61 | IX | .004-K1:(TP) DI10 | cooling water 1 = o.k. | .500/1.7 | T2
-K1 | DQ4 | QX_510_E1Ctrl | hot-air 1 = controller on | 0510/1.3 | 62 | QX | .004-K1:DQ4 | hot-air 1 = controller on | .510/1.3 | T1
-K20.16 | 0 | IW_510_B1Temp | hot-air PT100 | 0510/1.5 | 63 | IW | .004-K20.16:0 | hot-air PT100 | .510/1.5 | T2
-K1 | DQ5 | QX_510_Q1Heat | hot-air 1 = mains contactor on | 0510/1.6 | 64 | QX | .004-K1:DQ5 | hot-air 1 = mains contactor on | .510/1.6 | T1
-K1 | (TP) DI11 | IX_510_Q11Heat | mains contactor feedback 1 = o.k. | 0510/1.7 | 65 | IX | .004-K1:(TP) DI11 | mains contactor feedback 1 = o.k. | .510/1.7 | T2
-K1 | DQ6 | QX_511_K1AirInfeed | air infeed 0 = air infeed on | 0511/1.2 | 66 | QX | .004-K1:DQ6 | air infeed 0 = air infeed on | .511/1.2 | T1
-K2.03 | Q0.4 | QX_511_K2AirExhaust | exhaust 0 = exhaust on | 0511/1.3 | 67 | QX | .140-K2.03:Q0.4 | exhaust 0 = exhaust on | .511/1.3 | T1
-K2.04 | Q0.6 | QX_512_K1WorkPos. | hot-air head 1 = working position | 0512/1.2 | 68 | QX | .140-K2.04:Q0.6 | hot-air head 1 = working position | .512/1.2 | T1
-K2.11 | Q1.5 | QX_550_K1Blow | 1 = blow off clippings | 0550/1.2 | 69 | QX | .140-K2.11:Q1.5 | 1 = blow off clippings | .550/1.2 | T1
-K2.09 | Q1.0 | QX_610_K1GoodEject | good tube 1 = eject | 0610/1.2 | 70 | QX | .140-K2.09:Q1.0 | good tube 1 = eject | .610/1.2 | T1
-T4 | DI3 | IX_610_B1GoodEjectHome | good tube ejection 1 = home position | 0610/1.7 | 71 | IX | .007-T4:DI3 | good tube ejection 1 = home position | .610/1.7 | T2
-K20.1 | LED 4 | IX_611_B1TubePres | good tubes reject verification 1 = tube present | 0611/1.2 | 72 | IX | .004-K20.1:LED 4 | good tubes reject verification 1 = tube present | .611/1.2 | T2
-K2.10 | Q1.2 | QX_620_K1BadEject | bad tube 1 = eject | 0620/1.2 | 73 | QX | .140-K2.10:Q1.2 | bad tube 1 = eject | .620/1.2 | T1
-T4 | DI5/DQ1 | IX_620_B1BadEjectHome | bad tube ejection 1 = home position | 0620/1.7 | 74 | IX | .007-T4:DI5/DQ1 | bad tube ejection 1 = home position | .620/1.7 | T2
-K20.1 | LED 5 | IX_621_B1TubePres | bad tubes reject verification 1 = o.k. | 0621/1.2 | 75 | IX | .004-K20.1:LED 5 | bad tubes reject verification 1 = o.k. | .621/1.2 | T2
-K20.1 | LED 7 | IX_704_S1EStop | tube infeed emergency stop S1 1 = o.k. | 0704/1.2 | 76 | IX | .004-K20.1:LED 7 | tube infeed emergency stop S1 1 = o.k. | .704/1.2 | T2
-K20.1 | LED 6 | IX_704_B10Closed | TZF protective guarding B10 1 = o.k. | 0704/2.2 | 77 | IX | .004-K20.1:LED 6 | TZF protective guarding B10 1 = o.k. | .704/2.2 | T2
-K21.1 | LED 1 | IX_704_B1MaxBackup | tube conveyor light grid Receiver 1 = tubes present max.-backup | 0704/4.4 | 78 | IX | .004-K21.1:LED 1 | tube conveyor light grid Receiver 1 = tubes present max.-backup | .704/4.4 | T2
-K21.1 | LED 9 | QX_704_K1PushHomPos | pusher 1=forward | 0704/5.1 | 79 | QX | .004-K21.1:LED 9 | pusher 1=forward | .704/5.1 | T1
-K21.1 | LED 10 | QX_704_K2PushWorkPos | pusher 1=backward | 0704/5.3 | 80 | QX | .004-K21.1:LED 10 | pusher 1=backward | .704/5.3 | T1
-K21.1 | LED 2 | IX_704_B2PushHomePos | pusher forward | 0704/5.5 | 81 | IX | .004-K21.1:LED 2 | pusher forward | .704/5.5 | T2
-K21.1 | LED 3 | IX_704_B3PushWorkPos | pusher after | 0704/5.7 | 82 | IX | .004-K21.1:LED 3 | pusher after | .704/5.7 | T2
-K21.1 | LED 11 | QX_704_K3Brush | 1 = brush on | 0704/6.1 | 83 | QX | .004-K21.1:LED 11 | 1 = brush on | .704/6.1 | T1
-K21.1 | LED 4 | IX_704_B4PreWarnStorage | fill level monitoring prewarning | 0704/7.4 | 84 | IX | .004-K21.1:LED 4 | fill level monitoring prewarning | .704/7.4 | T2
-K21.1 | LED 5 | IX_704_B5PreWarnStorage | fill level monitoring prewarning | 0704/7.5 | 85 | IX | .004-K21.1:LED 5 | fill level monitoring prewarning | .704/7.5 | T2
-K21.1 | LED 3 | QX_511_K2AirInfeed | 0 = compressed air on | 0511/1.7 | 86 | QX | .004-K21.1:LED 3 | 0 = compressed air on | .511/1.7 | T1
-K20.17 | 0 | IW_511_B11ActFlow | flow air supply digit 1 | 0511/2.3 | 87 | IW | .004-K20.17:0 | flow air supply digit 1 | .511/2.3 | T2
-K20.17 | 1 | IW_511_B21ActFlow | flow air supply digit 2 | 0511/2.5 | 88 | IW | .004-K20.17:1 | flow air supply digit 2 | .511/2.5 | T2
-K20.17 | 2 | IW_511_B12ActFlow | flow exhaust digit 1 | 0511/3.3 | 89 | IW | .004-K20.17:2 | flow exhaust digit 1 | .511/3.3 | T2
-K20.17 | 3 | IW_511_B22ActFlow | flow exhaust digit 2 | 0511/3.5 | 90 | IW | .004-K20.17:3 | flow exhaust digit 2 | .511/3.5 | T2
-K21.2 | LED 9 | IX_512_B1RefIni | reference sensor lifter | 0512/1.8 | 91 | IX | .004-K21.2:LED 9 | reference sensor lifter | .512/1.8 | T2
-K2.16 | Q3.3 | QX_550_K1BlowTool | 1 = blow off clippings | 0550/1.2 | 92 | QX | .140-K2.16:Q3.3 | 1 = blow off clippings | .550/1.2 | T1
-K20.21 | LED 6 | QX_550_Q1Vacuum | extraction 1 = drive on | 0550/2.6 | 93 | QX | .004-K20.21:LED 6 | extraction 1 = drive on | .550/2.6 | T1
-K20.3 | LED 2 | IX_580_B1DataValid | Data valid | 0580/1.3 | 94 | IX | .004-K20.3:LED 2 | Data valid | .580/1.3 | T2
-K1 | O.03 | QX_580_B1Gate | 1 = gate | 0580/1.4 | 95 | QX | .004-K1:O.03 | 1 = gate | .580/1.4 | T1
-K20.3 | LED 3 | IX_580_B1Good | code reading 1 = good | 0580/1.4 | 96 | IX | .004-K20.3:LED 3 | code reading 1 = good | .580/1.4 | T2
-K20.3 | LED 4 | IX_580_B1Mismatch | code reading 1 = code bad signal | 0580/1.5 | 97 | IX | .004-K20.3:LED 4 | code reading 1 = code bad signal | .580/1.5 | T2
-K20.3 | LED 5 | IX_580_B1Bad | code reading 1 = bad | 0580/1.7 | 98 | IX | .004-K20.3:LED 5 | code reading 1 = bad | .580/1.7 | T2
-K20.3 | LED 6 | IX_580_B1Ready | code reading 1 = ready | 0580/1.8 | 99 | IX | .004-K20.3:LED 6 | code reading 1 = ready | .580/1.8 | T2
-K21.2 | LED 10 | IX_610_B1RefIni | reference sensor good tubes ejector 1 = bottom end position | 0610/1.8 | 100 | IX | .004-K21.2:LED 10 | reference sensor good tubes ejector 1 = bottom end position | .610/1.8 | T2
-K21.2 | LED 14 | IX_610_B11EjectHomePos | 1 = cylinder extended digit 1 | 0610/2.2 | 101 | IX | .004-K21.2:LED 14 | 1 = cylinder extended digit 1 | .610/2.2 | T2
-K21.1 | LED 14 | QX_610_K11EjectWorkPos | 1 = ejector good tubes digit 1 | 0610/2.3 | 102 | QX | .004-K21.1:LED 14 | 1 = ejector good tubes digit 1 | .610/2.3 | T1
-K21.2 | LED 15 | IX_610_B21EjectHomePos | 1 = cylinder extended digit 2 | 0610/2.6 | 103 | IX | .004-K21.2:LED 15 | 1 = cylinder extended digit 2 | .610/2.6 | T2
-K21.1 | LED 15 | QX_610_K21EjectWorkPos | 1 = ejector good tubes digit 2 | 0610/2.7 | 104 | QX | .004-K21.1:LED 15 | 1 = ejector good tubes digit 2 | .610/2.7 | T1
-K21.1 | LED 5 | IX_611_B11TubePres | countercheck discharge digit 1 1 = tube | 0611/1.2 | 105 | IX | .004-K21.1:LED 5 | countercheck discharge digit 1 1 = tube | .611/1.2 | T2
-K21.1 | LED 6 | IX_611_B21TubePres | countercheck discharge digit 2 1 = tube | 0611/1.4 | 106 | IX | .004-K21.1:LED 6 | countercheck discharge digit 2 1 = tube | .611/1.4 | T2
-K21.2 | LED 11 | IX_613_B1RefIni | reference sensor counter-support 1 = top end position | 0613/1.8 | 107 | IX | .004-K21.2:LED 11 | reference sensor counter-support 1 = top end position | .613/1.8 | T2
-K21.2 | LED 12 | IX_620_B1RefIni | reference sensor faulty tubes ejector | 0620/1.8 | 108 | IX | .004-K21.2:LED 12 | reference sensor faulty tubes ejector | .620/1.8 | T2
-K21.1 | LED 7 | IX_621_B11TubePres | countercheck discharge digit 1 1 = tube | 0621/1.2 | 109 | IX | .004-K21.1:LED 7 | countercheck discharge digit 1 1 = tube | .621/1.2 | T2
-K21.1 | LED 8 | IX_621_B21TubePres | countercheck discharge digit 2 1 = tube | 0621/1.4 | 110 | IX | .004-K21.1:LED 8 | countercheck discharge digit 2 1 = tube | .621/1.4 | T2
-K21.2 | LED 13 | IX_645_B1RefIni | reference sensor tube transfer | 0645/1.8 | 111 | IX | .004-K21.2:LED 13 | reference sensor tube transfer | .645/1.8 | T2
-K21.1 | LED 9 | QX_645_K1Vacuum | 1 = vacuum good tube transfer | 0645/3.2 | 112 | QX | .004-K21.1:LED 9 | 1 = vacuum good tube transfer | .645/3.2 | T1
-K21.1 | LED 10 | QX_645_K11Suck | 1 = tube suck in digit 1 | 0645/3.6 | 113 | QX | .004-K21.1:LED 10 | 1 = tube suck in digit 1 | .645/3.6 | T1
-K21.1 | LED 11 | QX_645_K11Blow | 1 = tube blow off digit 1 | 0645/3.7 | 114 | QX | .004-K21.1:LED 11 | 1 = tube blow off digit 1 | .645/3.7 | T1
-K21.1 | LED 12 | QX_645_K21Suck | 1 = tube suck in digit 2 | 0645/4.5 | 115 | QX | .004-K21.1:LED 12 | 1 = tube suck in digit 2 | .645/4.5 | T1
-K21.1 | LED 13 | QX_645_K21Blow | 1 = tube blow off digit 2 | 0645/4.7 | 116 | QX | .004-K21.1:LED 13 | 1 = tube blow off digit 2 | .645/4.7 | T1
-K20.1 | LED 6 | IX_720_A1Running | checkweigher 1 = running | 0720/1.3 | 117 | IX | .004-K20.1:LED 6 | checkweigher 1 = running | .720/1.3 | T2
-K20.1 | LED 7 | IX_720_A1Fault | checkweigher 1 = fault | 0720/1.4 | 118 | IX | .004-K20.1:LED 7 | checkweigher 1 = fault | .720/1.4 | T2
-K20.21 | LED 7 | QX_720_A1Auto | checkweigher automatic 1 = start / 0 = stop | 0720/1.4 | 119 | QX | .004-K20.21:LED 7 | checkweigher automatic 1 = start / 0 = stop | .720/1.4 | T1
-K20.1 | LED 8 | IX_720_A1TareNec | checkweigher 1 = Tara necessary | 0720/1.5 | 120 | IX | .004-K20.1:LED 8 | checkweigher 1 = Tara necessary | .720/1.5 | T2
-K20.21 | LED 8 | QX_720_A1Stop | checkweigher automatic 1 = stop | 0720/1.5 | 121 | QX | .004-K20.21:LED 8 | checkweigher automatic 1 = stop | .720/1.5 | T1
-K20.40 | 0 | QW_720_A1Speed | checkweigher target value rotation speed | 0720/1.7 | 122 | QW | .004-K20.40:0 | checkweigher target value rotation speed | .720/1.7 | T2
-K20.3 | LED 8 | IX_720_A1WeightPlus1 | checkweigher 1 = fill weight raise digit 1 | 0720/2.2 | 123 | IX | .004-K20.3:LED 8 | checkweigher 1 = fill weight raise digit 1 | .720/2.2 | T2
-K20.21 | LED 9 | QX_720_A1ResetFeedbCtrl | checkweigher 1 = reset feedback controls | 0720/2.2 | 124 | QX | .004-K20.21:LED 9 | checkweigher 1 = reset feedback controls | .720/2.2 | T1
-K20.3 | LED 9 | IX_720_A1WeightMinus1 | checkweigher 1 = fill weight lower digit 1 | 0720/2.3 | 125 | IX | .004-K20.3:LED 9 | checkweigher 1 = fill weight lower digit 1 | .720/2.3 | T2
-K20.3 | LED 10 | IX_720_A1WeightPlus2 | checkweigher 1 = fill weight raise digit 2 | 0720/2.4 | 126 | IX | .004-K20.3:LED 10 | checkweigher 1 = fill weight raise digit 2 | .720/2.4 | T2
-K20.3 | LED 11 | IX_720_A1WeightMinus2 | checkweigher 1 = fill weight lower digit 2 | 0720/2.5 | 127 | IX | .004-K20.3:LED 11 | checkweigher 1 = fill weight lower digit 2 | .720/2.5 | T2
-K1 | O.02 | QX_810_A1Trigger | release printer | 0810/2.5 | 128 | QX | .004-K1:O.02 | release printer | .810/2.5 | T1
-K20.3 | LED 7 | IX_810_A1Ready | Ink-Jet ready for operation | 0810/2.8 | 129 | IX | .004-K20.3:LED 7 | Ink-Jet ready for operation | .810/2.8 | T2
-K21.1 | LED 4 | IX_810_B2Collision | 0 = Inkjet-printer in collision position | 0810/3.2 | 130 | IX | .004-K21.1:LED 4 | 0 = Inkjet-printer in collision position | .810/3.2 | T2
-K30.1 | LED 0 | IX_1003_S2On | 1 = machine start | 1003/1.4 | 131 | IX | .004-K30.1:LED 0 | 1 = machine start | .1003/1.4 | T2
-K30.1 | LED 1 | IX_1003_S3Off | 0 = machine stop | 1003/1.5 | 132 | IX | .004-K30.1:LED 1 | 0 = machine stop | .1003/1.5 | T2
-K30.20 | LED 0 | QX_1003_P1On | 1 = machine is running | 1003/1.6 | 133 | QX | .004-K30.20:LED 0 | 1 = machine is running | .1003/1.6 | T1
-K30.1 | LED 2 | IX_1005_B1CompAir | compressed air 1 = o.k. | 1005/1.2 | 134 | IX | .004-K30.1:LED 2 | compressed air 1 = o.k. | .1005/1.2 | T2
-K30.1 | LED 3 | IX_1100_B1RefIni | reference sensor TZ box chain transport rail 1 = electrical reference position | 1100/1.6 | 135 | IX | .004-K30.1:LED 3 | reference sensor TZ box chain transport rail 1 = electrical reference position | .1100/1.6 | T2
-K30.1 | LED 4 | IX_1100_B2BoxPres | box sensing 1 = carton present | 1100/1.7 | 136 | IX | .004-K30.1:LED 4 | box sensing 1 = carton present | .1100/1.7 | T2
-K30.1 | LED 5 | IX_1141_T1DCOK | power supply Interroll 1 = OK | 1141/1.4 | 137 | IX | .004-K30.1:LED 5 | power supply Interroll 1 = OK | .1141/1.4 | T2
-K30.1 | LED 6 | IX_1145_B4PocketClear | release Transfer pusher 1 = empty | 1145/2.8 | 138 | IX | .004-K30.1:LED 6 | release Transfer pusher 1 = empty | .1145/2.8 | T2
-K30.1 | LED 7 | IX_1200_B1RefIni | reference sensor TZ main drive 1 = electrical reference position | 1200/1.7 | 139 | IX | .004-K30.1:LED 7 | reference sensor TZ main drive 1 = electrical reference position | .1200/1.7 | T2
-K30.1 | LED 8 | IX_1201_B1Overload | pick up finger overload 1 = o.k. | 1201/1.2 | 140 | IX | .004-K30.1:LED 8 | pick up finger overload 1 = o.k. | .1201/1.2 | T2
-K30.20 | LED 1 | QX_1201_K1ShiftWorkPos | 1 = coil on pick up finger shifting | 1201/1.7 | 141 | QX | .004-K30.20:LED 1 | 1 = coil on pick up finger shifting | .1201/1.7 | T1
-K30.1 | LED 9 | IX_1300_B1MinSupply | tube conveyor 1 = tubes present | 1300/1.5 | 142 | IX | .004-K30.1:LED 9 | tube conveyor 1 = tubes present | .1300/1.5 | T2
-K30.1 | LED 10 | IX_1300_B2PlacePosClear | tube conveyor cast off release 1 = release | 1300/1.7 | 143 | IX | .004-K30.1:LED 10 | tube conveyor cast off release 1 = release | .1300/1.7 | T2
[5 empty] | 144 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 145 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 146 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 147 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 148 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 149 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 150 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 151 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 152 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 153 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 154 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 155 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 156 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 157 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 158 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 159 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 160 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 161 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 162 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 163 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 164 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 165 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 166 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 167 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 168 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 169 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 170 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 171 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 172 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 173 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 174 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 175 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 176 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 177 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 178 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 179 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 180 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 181 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 182 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 183 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 184 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 185 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 186 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 187 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 188 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 189 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 190 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 191 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 192 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 193 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 194 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 195 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 196 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 197 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 198 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 199 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 200 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 201 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 202 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 203 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 204 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 205 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 206 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 207 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 208 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 209 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 210 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 211 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 212 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 213 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 214 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 215 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 216 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 217 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 218 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 219 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 220 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 221 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 222 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 223 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 224 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 225 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 226 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 227 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 228 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 229 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 230 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 231 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 232 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 233 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 234 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 235 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 236 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 237 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 238 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 239 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 240 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 241 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 242 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 243 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 244 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 245 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 246 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 247 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 248 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 249 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 250 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 251 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 252 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 253 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 254 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 255 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 256 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 257 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 258 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 259 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 260 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 261 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 262 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 263 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 264 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 265 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 266 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 267 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 268 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 269 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 270 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 271 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 272 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 273 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 274 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 275 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 276 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 277 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 278 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 279 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 280 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 281 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 282 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 283 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 284 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 285 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 286 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 287 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 288 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 289 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 290 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 291 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 292 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 293 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 294 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 295 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 296 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 297 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 298 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 299 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 300 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 301 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 302 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 303 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 304 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 305 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 306 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 307 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 308 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 309 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 310 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 311 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 312 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 313 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 314 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 315 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 316 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 317 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 318 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 319 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 320 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 321 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 322 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 323 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 324 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 325 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 326 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 327 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 328 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 329 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 330 | #VALUE! | .004: | 0 | #N/A | #VALUE!
[5 empty] | 331 | #VALUE! | .004: | 0 | #N/A | #VALUE!

## NEW 1 (hidden)
Abs. Operand | Ort | Busmodul | Sym. Operand | Address | Kommentar | Page | Page | Test
IX_000_CB | 0000/3.2 | -K20.1 | LED 0 | 004-K20.1:LED 0 | Sicherungsautomaten 1 = nicht in Ordnung | 000/3.2 | #VALUE!

## Old
Abs. Operand | Ort | Busmodul | Sym. Operand | Ort | Formular | Address | Kommentar | Page | Test
IX_000_CB | 0000/3.2 | -K20.1 | LED 0 | 0044/5.9 | 004 | 004-K20.1:LED 0 | Sicherungsautomaten 1 = nicht in Ordnung | 000/3.2 | T2 | 1